## bugs-2008-08-05-1
bug_id | bug_severity | priority | assigned_to | short_short_desc | Sizing | Sizing(PW)
242688 | normal | P1 | sleeloy@ca.ibm.com | Under IE, refreshing COSMOS UI produces - Multiple Loading DataManagers icon | Low | 0.4
238345 | major | P2 | martin.simmonds@ca.com | Problems with the tabular graph response view | Medium | 1
238227 | normal | P2 | martin.simmonds@ca.com | COSMOSUI tests - GraphResponseViewer, Problem with Record Details Dialog | Low | 0.2
242556 | normal | P2 | sleeloy@ca.ibm.com | GraphResponseViewer for Hierarchical View does not show errors for invalid queries | Low | 0.4
223241 | normal | P3 | martin.simmonds@ca.com | Full screen mode toolbar button | Low | 0.4
224169 | normal | P3 | martin.simmonds@ca.com | Ability to resize dialog box. | Low-Medium | 0.6
237008 | normal | P3 | martin.simmonds@ca.com | Tree viewer has Replaced the Tabular viewer as Default | Low-Medium | 0.6
237009 | normal | P3 | martin.simmonds@ca.com | When the OPEN WITH is selected it should remain the default | Low-Medium | 0.6
222709 | normal | P3 | sleeloy@ca.ibm.com | QueryBuilder should populate the MdrID | Low | 0.2
236721 | normal | P3 | sleeloy@ca.ibm.com | General Internationalization | Low | 0.2
242110 | normal | P3 | sleeloy@ca.ibm.com | Should show progress icon when submitting a query to an MDR | Low | 0.2
241813 | normal | P3 | todjo06@ca.com | Launching the COSMOS UI with a MDR query and using OpenWith | Low-Medium | 0.6
240980 | normal | P4 | sleeloy@ca.ibm.com | Folder Icon should change. | Low | 0.2
bug_id | bug_severity | priority | assigned_to | short_short_desc | Sizing | Sizing(PW)
237655 | enhancement | P3 | sleeloy@ca.ibm.com | Provide a reporting service group for data managers | High | 2
241815 | enhancement | P2 | sleeloy@ca.ibm.com | UI should use the securityNamespace to prompt for credentials | Low-Medium | 0.8
229800 | enhancement | P2 | todjo06@ca.com | Provide DOJO simple method descriptions for services available in COSMOS | Medium | 1
230405 | enhancement | P2 | sleeloy@ca.ibm.com | Create a Report based on CMDBf information | Low-Medium | 0.6
Notes: | Reassign 241815
Possibly move 237655 to future as it cannot be contained